## Sprint Backlog
Sprint Back Log
Task ID | Task | Description | Story ID | Backlog ID | Sprint# | State | Estimate Time (Hours) | Assign to | Note
SMS Manage
T01 | Draw Usecase SMS |  |  | PB01 |  | New | 40 | Huy Hưng
T02 | Analyse and design code SMS |  |  |  |  | New | 40 | Huy Hưng
T03 | Code : Update start date and end date of single quarantee period |  | RQ04 |  | 1 | New | 10 | Hưng
T04 | Code: Set up SMS form |  |  |  | 1 | New | 2 | Hưng
T05 | Code: Send SMS |  | RQ05 |  | 1 | New | 25 | Huy
T06 | Code: Save SMS list , which have been sent for customer |  | RQ10 |  | 1 | New | 20 | Hưng
T07 | Code: View SMS list, which have been sent for customer |  |  |  | 1 | New | 10 | Hưng
T08 | Set up, update time to send SMS and time to stop send SMS |  |  |  | 1 | New | 30 | Hưng
T09 | Integrate All functions SMS | [5 empty] | 10 | Huy Hưng
T10 | Implement Unit Test , Integrated Test , System Test SMS |  |  |  | 1 | New | 30 | Huy Hưng
Customer Manage
T11 | Draw Usecase Customer Manage |  |  | PB02 |  |  | 20 | Tuấn
T12 | Analyse and design codeCustomer Manage | [5 empty] | 20 | Tuấn
T13 | Code: Import customer from excel format |  | RQ02 RQ03 |  | 1 | New | 20 | Tuấn Thắng
T14 | Code: Add new customer |  |  |  | 1 | New | 15 | Tuấn
T15 | Code: Update customer |  |  |  | 1 | New | 10 | Tuấn
T16 | Code: Disable customer |  |  |  | 1 | New | 5 | Tuấn
T17 | Code: Find Customer |  |  |  | 1 | New | 10 | Tuấn
T18 | Code: Set up time range that user can view list of customer birthday |  | RQ07 |  | 1 | New | 15 | Tuấn Thắng
T19 | Code: Print recent BirthDay Customer list |  |  |  | 1 | New | 20 | Tuấn Thắng
T20 | Code: View recent BirthDay Customer list |  |  |  | 1 | New | 5 | Tuấn Thắng
T21 | Integrate All functions Customer Manage |  |  |  | 1 | New | 5 | Tuấn Thắng
T22 | Implement Unit Test , Integrated Test , System Test Customer Manage |  |  |  | 1 | New | 20 | Tuấn Thắng
Motor Type Manage
T23 | Draw Usecase Motor type Manage |  |  | PB03 |  |  | 10 | Phúc
T24 | Analyse and design code Motor type Manage | [5 empty] | 20 | Phúc
T25 | Code: Add new motor type |  | RQ08 |  | 1 | New | 10 | Phúc Phương
T26 | Code: Update new motor type |  |  |  | 1 | New | 10 | Phúc Phương
T27 | Code: Find motor type Function |  |  |  | 1 | New | 10 | Phúc Phương
T28 | Code: Disable motor type |  |  |  | 1 | New | 10 | Phúc Phương
T29 | Integrate All functions Motor type Manage |  |  |  | 1 | New | 5 | Phúc Phương
T30 | Implement Unit Test , Integrated Test , System Test Motor type Manage |  |  |  | 1 | New | 20 | Phúc Phương
Motor Manage
T31 | Draw Usecase Motor Manage | [5 empty] | 10 | Phúc
T32 | Analyse and design code Motor Mange | [5 empty] | 20 | Phúc
T33 | Code: Create motor |  | RQ08 | PB03 | 1 | New | 10 | Phúc
T34 | Code: Update motor |  |  |  | 1 | New | 10 | Phúc
T35 | Code: Find motor Function |  |  |  | 1 | New | 5 | Phúc
T36 | Code: Disable motor type |  |  |  | 1 | New | 5 | Phúc
T37 | Code: Create new color of motor |  |  |  | 1 | New | 10 | Phúc Phương
T38 | Code: import motor from excel format | [5 empty] | 10 | Phúc Phương
T39 | Integrate All functions Motor Manage |  |  |  | 1 | New | 15 | Phúc Phương
T40 | Implement Unit Test , Integrated Test , System Test Motor Manage |  |  |  | 1 | New | 20 | Phúc Phương
All Package Comple
T41 | Imtegrate all package | [5 empty] | 30 | All Member
T42 | Implement Integrate Test | [5 empty] | 15 | All Member
T43 | Implement System Test. | [5 empty] | 25
Before start sprint
T44 | Test plan | [5 empty] | 6 | Phương
T45 | Training Plan | [5 empty] | 1 | Huy
T46 | Traning | [5 empty] | 20 | Thắng Huy
T47 | Project Plan | [5 empty] | 30 | Huy
T48 | Master Plan | [5 empty] | 10 | Huy
T49 | Analyse Data base | [5 empty] | 6 | Hưng
T50 | Draw ERD | [5 empty] | 7 | Hưng
T51 | Code SQL | [5 empty] | 20 | Hưng
T52 | main GUI | [5 empty] | 2 | Thắng
T53 | Quality Attribute | [5 empty] | 10 | Phương
T54 | Scope and Vision | [5 empty] | 3 | Phương
T55 | Constraint | [5 empty] | 3 | Phương
T56 | Customer Process | [5 empty] | 6 | Phương
T57 | Product backlog | [5 empty] | 4 | Phương
T58 | Write Sprint backlog | [5 empty] | 10 | Phương Thắng
T59 | Manage Burn Down Chart | [5 empty] | 15 | Thắng

## Release Backlog
Backlog ID | Backlog | STORY / FEATURE / REQUEST |  |  | Story ID | Priority | Business Value | Sprint# | State | Note
|  | As a/an [User role] | I want to [Goal] | So that [reason]
PB01 | Quan ly tin nhan | User | Set the start time, end time, and content will be sent SMS messages | I can remind customers to car maintenance in each time | RQ04 | 1 | High | 1 | New
|  | User | Have the program which automatically send a message each day | I can announce to customer who have enough conditions in the RQ04 and is not sended messages about my vehicle maintenance program | RQ05 | 1 | High | 1 | New
|  | User | Send the message to all my customer | We can send a message again when it has been error | RQ06 | 1 | High | 1 | New
|  | User | Review the history of messages sent to customers. | I know my program which implement well and all my customer know it | RQ10 | 3 | Medium | 1 | New
PB02 | Quan ly thong tin khach hang | User | Print a list of customers coming to the birthday | We can send a birthday card or a birthday message | RQ07 | 3 | High | 1 | New
| Quan ly thong tin khach hang | User | View my customer's information which like SMS Template.xls | I can manage the information of customer who buy my motorbikes | RQ02 | 2 | Medium | 1 | New
| Quan ly thong tin khach hang | User | Import my customer's information from file excel (like SMS Template.xls) | I can create the list of customer's information quickly | RQ03 | 2 | High | 1 | New
PB03 | Quan ly xe | User | View my motorbike's information include : categories, colors, price, inventory | I can manage the information of motorbike in my superstore | RQ08 | 3 | High | 1 | New

## Product Backlog
ID | STORY / FEATURE / REQUEST |  |  | Priority | Business Value | Acceptance Criteria | State | Note
| As a/an [User role] | I want to [Goal] | So that [reason]
RQ01 | User | Tôi muốn một ứng dụng giúp quản lý thư viện có một giao diện hiện đại. | Người quản lý thư viện có thể dễ dàng quản lý sách và việc mượn trả sách. |  |  |  | New
RQ02 | User | Tôi muốn người dùng có thể đăng kí và đăng nhập. | Giúp người quản lý có thể quản lý sách trong thư viện, giúp lưu trữ lịch sử mượn, trả sách của mỗi người dùng. |  |  |  | New
RQ03 | User | Tôi muốn người dùng có thể tạo một thư viện sách. | Nơi lưu trữ tên, thông tin, địa chỉ thư viện và list sách. |  |  |  | New
RQ04 | User | Tôi muốn thêm sách và thông tin sách, số lượng vào danh sách. | Người quản lý dễ dàng cập nhật các đầu sách mới có trong thư viện. |  |  |  | New
RQ05 | User | Tôi muốn chỉnh sửa và xóa sách trong list. | Người quản lý dễ dàng cập nhật các đầu sách không còn trong thư viện. |  |  |  | New
RQ06 | User | Tôi muốn có hiển thị list sách. | Người mượn sách có thể xem thông tin về sách mà không cần tốn thời gian đến thư viện để tìm hiểu. |  |  |  | New
RQ07 | User | Tôi muốn tìm kiếm sách theo tên. | Người mượn sách có thể dễ dành hơn trong việc chọn sách để mượn. |  |  |  | New
RQ08 | User | Tôi muốn tìm kiếm thư viện theo tên. | Người dùng dễ dàng tiếp cận thông tin sách có trong các thư viện. |  |  |  | New
RQ09 | User | Tôi muốn hiển thị lịch sử mượn sách, trả sách. | Giúp thống kê sách đã trả và sách chưa trả. |  |  |  | New
RQ10 | User | Tôi muốn phân chia sách theo thể loại. | Người mượn sách dễ dàng tìm kiếm những cuốn sách theo thể loại mình mong muốn. |  |  |  | New
RQ11 | User | Tôi muốn hiển thị danh sách sách mới. |  |  |  |  | New
RQ12 | User | Tôi muốn có tính năng phân loại, hiển thị sách quá hạn trả. |  |  |  |  | New

## RULE
Title: Brief description of the PBI. The title of a PBI should represent the intent of the PBI.
Iteration: Indicate the sprint in which a PBI is implemented. When you first enter a PBI into TFS, iteration defaults to the current project, meaning that it's not yet scheduled for a sprint. During the sprint planning meeting, when the team commits to implementing a PBI, you set this field to the iteration representing the sprint.
Assigned To: Indicates the owner of a PBI. The product owner who's assigned to the PBI is responsible for answering questions and providing details about the PBI. This person is also responsible for verifying that the PBI meets acceptance criteria before the team finishes the sprint. When a PBI is first created, the Assigned To field defaults to the user entering the PBI, so it's best to set it to the product owner at that point.
State: Use the State field to track the current state of a PBI.
New: The PBI is entered into TFS. It may be just the initial text of a user story, or it may be fully defined with test cases and acceptance criteria.
Approved: The PBI has been approved by the product owner and is a candidate to be assigned to a sprint at the sprint planning meeting.
Committed: The PBI has been assigned to a sprint, and the team has committed to completing it.
Removed: The PBI is no longer needed. This is useful when you're pruning the backlog to remove duplicates, to consolidate similar PBIs, or to simply remove the PBIs that are such low priority that they will never be built.
Done: The PBI is complete, and the product owner has tested and verified it.
Reason: Reason is a read - only field that is predefined based on the state and transition of the PBI.
New
New Backlog Item : The PBI was just entered but not yet prioritized or estimated.
Reconsidering Backlog Item : The item had been removed but was reconsidered and is now back in the backlog.
Approved
Approved by the Product Owner : The PBI was approved by the product owner and is now ready to be included in a sprint.
Work Stopped : The PBI had been committed to a sprint, but the team decided to stop work on it and put it back in the backlog for future sprint.
Committed : Commitment Made by the Team : The team has committed to implement the PBI in a sprint.
Additional Work Found: The PBI was previously considered done, but more work was found, so it's back in the backlog.
Removed: The PBI was removed from the backlog.
Done: The work on the PBI is finished.
Backlog Priority: Used to determine the position of the PBI on the product backlog. New PBIs default to a backlog priority of 1,000. This field represents an item's location in the backlog, not its business value. It indicates when the PBI should be scheduled, relative to other items on the list.
Effort: Used to track the estimated effort required to implement a PBI, relative to other PBIs in the release. Relative is the operative word here, as the effort is not in terms of hours or days. Rather, it's a just a number used to compare the relative effort required for PBIs.
Business Value: Used to track the amount of business value delivered by a PBI. You should choose a number between 1 and 100 to represent the amount of business value that implementing the PBI will deliver to your customers. Higher numbers imply greater business value. A PBI with a low business value and a high effort estimate probably won't get scheduled into a sprint and will remain on the product backlog.
Description: Used to provide a detailed description of a PBI. This is where the product owner describes what the feature does and who needs it. If you're defining PBIs via user stories, then this is the written record of the feature.
Acceptance Criteria: Used to provide a bulleted list of criteria a PBI must meet before it will be accepted as done. The product owner defines the acceptance criteria either when initially creating the PBI or when the PBI is added to a sprint. It's critical to have sufficient information in this field for a PBI because these are the criteria against which the team will build the feature during the sprint.
Conclusion
In this article, we have seen that the product backlog is the list of requirements for the system. It is the central focus of a Scrum team, representing the features that the team will build into the product. The product owner defines and prioritizes the PBIs. Each PBI stores the details of one product feature. It describes its business benefit, test cases, and acceptance criteria.